## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | Event Recommendation System
PROJECT ID
PROJECT MANAGER | Jayanth G S
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2020-06-15 | Project title and description | Software | Problem in interpreting problem statement correctly | Query solved by asking on workgroup | Read and undertood about general Natural Language Processing(NLP) and its projects in movie recommendation, etc. | Vinit Kanse | Complete
2 | 2020-06-27 | Training Data Set | Software | Need of creating big dataset to train the model | Discussed with college professors | Started creating dataset by refering Google for Events | Vinit Kanse | Complete
3 | 2020-07-10 | Machine Learning approch to deal with text data | Software | Less knowledge of NLP and textual data result into delay in submitting | Googled NLP | Enrolled in NLP couse on coursera and got my doubts cleared . | Vinit Kanse | Complete
4 | 2020-07-25 | Documentation | Project Mangement | None | Activities and updates by Jayanth sir | Completed all the required project documents | Vinit Kanse | Complete