## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Event Recommendation System
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-07-07
PROJECT DELIVERABLE |  |  | EXECUTION PHASE END DATE: |  | 2020-07-31
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | In-Progress
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
Planning | Documentation |  | 2020-06-15 | 2020-07-01 | 16 | COMPLETED
Data Set Creation | Dataset for training ML model |  | 2020-06-25 | 2020-07-10 | 16 | COMPLETED
Execution | Program code |  | 2020-07-07 | 2020-07-27 | 20 | COMPLETED
| Test runs and corrctions |  | 2020-07-21 | 2020-07-30 | 9 | COMPLETED
| Final documentation |  | 2020-07-30 | 2020-07-31 | 2 | COMPLETED