## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0
| Project title: | Event Recommendation System |  | Project Id: |  | Project Manager: | Jayanth G S |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 29-07-2020 | Project Team Lead: | Aarya Bodhankar |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 5 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Events involving with multiple domain and events in a single instant. | Different domains within a single instant would me missed out. | Take into consideration all permutation and combinations. | Project Manager | High |  | Closed | Risk
2 | Risk | Irrelevant events which are not of use to employees gets fed in the dataset | Bad recommendation of employees | Have a relevant events which is of interest or domain of employees | Project Manager | Moderate |  | Closed | Assumption
3 | Assumption | The domains of employees is correct in which they are working or having interest | The events get recommended accurately. | Have a well crossed checked before analysis | Project Manager | Moderate |  | Closed | Issue
4 | Issue | Low Accuracy of the model | Impact on the recommendation | Get adequate data and choose perfect model | Project Manager | High |  | Closed | Dependency
5 | Issue | Inadequate data for training the model | Bad recommendation of employees | Get adequate data and choose perfect model | Project Manager | Moderate |  | Closed
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24